[image: image1.wmf]
[image: image2.wmf]

LCN+ Cycle Route Implementation and Stakeholder Plan (CRISP)

Project Brief

Items in italics to be completed by the Client.

Introduction

Describe the Link location and broad context in terms of land use, road traffic and cycling and identify any specific relevant reports or other information to be taken into account.

Purpose of Commission

The purpose is to undertake a systematic review of the existing conditions for cycling on Link number XX, taking full account of local knowledge, constraints and concerns. Route alignment, issues, opportunities and constraints (physical and institutional) are to be considered in conjunction with stakeholders. 

Recommendations for a route strategy and practical measures most likely to be successful in attracting and maintaining substantial cycle flows will be made. Budget cost estimates and a provisional outline programme will be prepared.

Recommendations could include detailed technical feasibility studies, modelling, surveys etc. which in themselves are not part of this brief.

The Final CRISP report is strategic and should avoid detailed consideration of treatments which will follow on from the CRISP study during design development.

London Cycling Design Standards

When considering strategy and treatment options, the content of the London Cycling Design Standards (TfL, May 2005) is to be taken into account. The principles of providing continuous, safe and comfortable conditions for cycling, with minimal delay to cycle journey times should be followed.

Opportunities and Constraints

Constraints including geographical/landscape barriers, link and junction capacity and competing priorities for road space must be allowed for. 

In assessing options and costs and making recommendations the requirements and practicalities for implementation, maintenance and enforcement are to be taken into account.

Outputs
The following documents are to be prepared in accordance with the  specification in Annex 1 to this brief.

· Pre-CRIM Report

· Record of CRIM

· Draft CRISP Report

· Final CRISP Report

Reports shall be issued to CRIM Stakeholders as set out in the brief.
Appropriate procedures should be in place for checking and quality assurance of reports.

Paper copies should be provided. Provision of copies of reports electronically (e.g. on CD) should be arranged between the client and consultant at the Inception meeting and with CRIM Stakeholders (for Draft and Final CRISP Reports at the CRIM stage)

Methodology / Sequence

Stage 1 – Preparation, data collection, summary and dissemination

· Inception Meeting with Client to discuss brief and agree programme.

Client to hand over information to consultant (see list below under ‘information to be provided by client’)

· Finalise a schedule of CRIM and Other Stakeholders (see below for guidance) with contact details (Client to prepare draft schedule)

· Issue questionnaire to Other Stakeholders within 1 week of the start of the commission with a deadline for responses of a maximum of 5 weeks from date of issue(See Annex 2 for example letter and questionnaire). 
· Commence liaison with CRIM stakeholders to inform them of the study and suggest and agree dates for the CRIM

· Obtain available data on cycle flows (including joining/leaving and crossing the Link), and cycle accidents (last 3 years).

If cycle flow information is not available from the Client, the LCN+ Project Management office at London Borough of Camden may be able to provide appropriate data. Simple counts may be necessary to provide basic existing cycle flow data if pre-existing information is not available. Requirements and method for collecting data should be agreed with the client.
· Obtain available data on motor vehicle flows, turning movements, speeds, HGV and bus flows/proportions, link and junction capacity

· Review pedestrian amenity on the Link and pedestrian/cycle interface issues, such as footway cycling concerns

· Record existing characteristics on the Link including:

· Major trip generators, including bus and rail stations, educational establishments, major employers, retail centres, hospitals and leisure uses
· broad land use, frontage activity, bus stops, parking and loading facilities and restrictions

· carriageway, footway and other widths, relevant highway boundaries

· existing facilities for cyclists including extent and widths of lanes, tracks and paths (noting whether on or off-carriageway), Advanced Stop Lines, crossing facilities, cycle exemptions from traffic restrictions, ease of access on and off the Link
· existing problems for cyclists including pinchpoints, discontinuities, 
deviations, narrow tracks, poor surface, ponding, unclear facilities, 
legal restrictions, enforcement issues, (for examples see LCDS 1.1.22)
· Review and summarise the information provided by the Client (see list below).
· Agree with the client  alternative routes to be studied, taking into account:

· views of CRIM stakeholders

· responses to questionnaires
· routes shown on London Cycle Guide maps

· Provisional division of Links into Sections of similar characteristics defined by factors such as traffic flow, speed limit/recorded speeds, gradient, land use, frontage activity (including parking and loading), corridor/carriageway width with the objective of providing consistent solutions on each Section
· Prepare Pre-CRIM Report. This forms the basis for Parts 1.1 to 4.1 of the Draft CRISP Report 

· Issue the pre-CRIM report and the formal invitation to the CRIM to CRIM Stakeholders at least 2 weeks before the CRIM ( the dates of the CRIM and pre-CRIM meeting should have been informally agreed with CRIM Stakeholders in advance of this date)

See Annex 3 for an example Pre-CRIM Report issue letter

· During the week preceding the CRIM, hold a pre-CRIM meeting* to agree the scope, practical arrangements (e.g. meeting point, lunch stop and a timetable for the day) for the CRIM with the Client and CRIM invitees.

A practical approach to the timing and duration of the pre-CRIM meeting is required to accommodate voluntary sector attendants. A meeting late in the afternoon of no more than two hours duration is suggested.

*Subject to the agreement of the CRIM Stakeholders (excluding CCE), a pre-CRIM meeting is not necessary if the objectives of the meeting can be met by other means.

Stage 2 – Cycle Route Inspection Meeting (CRIM)

· Consultant to host the CRIM. Arrangements for the day must be made in advance with the CRIM Stakeholders.
· The CRIM should not take place without the attendance of a representative of the relevant highway authority(ies). This would preferably be the borough cycle officer and a senior officer from the highways department

· Representatives from neighbouring/adjoining authorities should be invited to attend the CRIM at the relevant location (s)

· All reasonable effort should be made to ensure that a representative from LCC and/or CTC or local cyclists’ stakeholder groups attends the CRIM.

· The CRIM should take place on bicycles or on foot.

A suggestion is to first cycle the whole Link from one end to the other then return along the Link, stopping to consider specific locations. It is desirable for at least part of the CRIM to take place during a weekday peak period.
· Issue a “Record of CRIM” to all invitees within 2 weeks of it taking place (This to form Appendix A to the Final CRISP Report)

Stage 3 – Prepare & issue Draft CRISP Report 

(See Annex 1 for format and detailed content)

· Refer to the London Cycling Design Standards (LCDS)
· Review the information obtained during Stages 1 and 2  and develop strategy options for each Section/Element in conjunction with the Client, involving Other Stakeholders as appropriate

(Refer to LCDS Figure 2.3 for guidance for on-carriageway options)
· Assess the strategy options in terms of their advantages, disadvantages, and feasibility. 
· Where options could take a long period to implement, short term improvements for cycling could also be recommended.
· Prepare budget costs for options

· Recommend preferred option with reasons

· Allocate the recommended options to a programme year

(The need for close liaison between the consultant and highway authority and LCN+ project management team (LB Camden) regarding budget costs and outline programme is emphasised to produce realistic and achievable outcomes)

· Compile Draft CRISP Report

· Issue Draft CRISP Report to CRIM stakeholders within 4 weeks of the CRIM, with deadline for comments of 2 weeks

· Arrange Review of Draft CRISP Report meeting with CRIM and any other appropriate stakeholders within 1 week of issue of the report
nb All significant issues should have been discussed prior to and reflected in the Draft CRISP Report. The purpose of this meeting is to consider minor amendments to report content and the inclusion of additional relevant information.
Stage 4 – Prepare and Issue Final CRISP Report

· Revise the Draft CRISP Report to produce the Final CRISP Report taking into account comments received on the draft report and matters raised at the Draft Report Review meeting

· Issue the Final CRISP Report to the CRIM Stakeholders (two copies to the Client) within 2 weeks of the Review of Draft CRISP Report meeting referred to in Stage 3

Stakeholders

The Stakeholders will be identified by the Client during Stage 1 and will be split into two groups: 

1.
The CRIM Stakeholders:

· Highway authority representative  i.e. 

- the borough cycling officer and senior highways department officer(and/or leisure/parks department where appropriate) for Links on borough roads or 

- TfL Area Team officer for Links on TLRN

· The borough cycle officer for Links on the TLRN

· London Borough of Camden LCN+ Project Management team

· TfL Area Team for Links  on borough roads that interface or affect the Transport for London Road Network

· London Cycling Campaign local representative and/or other local cycling group representatives such as Cyclists Touring Club (CTC)
(LCC borough group contacts can be found by following the link to “borough groups” on the LCC website at www.lcc.org.uk)

· Sustrans - where the route is on or interfaces with a National Cycle Network route or where a local Sustrans supporter has been identified (Sustrans Head Office to liaise with LCN+ project management on this matter)

· TfL Cycling Centre of Excellence (note: CCE will not normally attend CRIMs but should be invited and be issued the pre-CRIM Report for information and monitoring purposes)

· Representatives from neighbouring/adjoining authorities (e.g. boroughs, TfL, parks department etc.) should be invited to attend the CRIM at the relevant location (s)

2.
Other Stakeholders (who will be sent the Questionnaire). This list of 
examples may not be exhaustive:

· ward councillors along the Link

· lead member for environment

· head of borough planning department
· local Police, 

· TfL London Buses (Bus Priority Projects and Bus Operations)

· TfL signals (NID), 

· Cycling group representatives in neighbouring borough (s)

· London Transport Users Committee (LTUC)

· town centre managers, 

· educational establishments, 

· major hospitals

· sports stadia

· residents groups,
· non-cycling user groups(e.g. representatives of mobility impaired or pedestrians)
· petitioners, 

· major employers, 

· traders representatives, 

· affected landowners (e.g. Royal Parks Authority, British Waterways, Corporation of London where open spaces affected are under their control (e.g. Epping Forest))

Meetings

The following meetings (excluding the CRIM) should be allowed for:

· Inception meeting

· Pre-CRIM meeting
· Review of Draft CRISP Report meeting
The consultant will arrange, prepare agendas and take minutes of these meetings and distribute them to CRIM stakeholders. Arrangements for hosting  meetings are to be agreed with the Client.  The client will chair all meetings.
Additional meetings between the Client and consultant to be arranged as required.

Information to be provided by the Client at the Inception Meeting
The following information is to be provided by the Client at the Inception meeting (in either hard or electronic copy (e.g. CD)):

· Draft schedule of CRIM stakeholders and Other Stakeholders, with contact details where known

· Copies or extracts of existing relevant documents such as previous reports and correspondence. 

These should include, where relevant, the following previously commissioned LCN reports (if the Client does not hold copies they are available for inspection at LCN+ Project Management at LB Camden):

· Quality Monitoring reports

· Sector Consultant reports on Priority Strategic Routes

· Major services plant that could influence options

· Schedule of other schemes and/or studies that may affect the Link

· Schedule of current/programmed public or private sector developments that could have a direct or indirect impact on the Link

Programme

The time-scale for completion of the commission is XX weeks from award to issue of the Final CRISP Report. The consultant shall submit their programme for agreement within 5 working days of the Inception meeting.
An indicative programme based on the time periods stated in this brief is attached in Annex 5. The minimum periods stated in this brief may be extended by agreement with the client.

Financial

The target budget for this commission is £XXXX. 

Describe invoicing arrangements (it is suggested that invoices are accepted as each milestone is achieved)
CRISP GENERIC BRIEF TOOL-KIT V2
CRISP BRIEF V2.doc

